## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration (Days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Project Charter
Research data points on existing restaurant systems |  |  |  | 3 | bar: WEEK 1 M to WEEK 1 W
Get historical data on ordering and payment systems of the restaurant |  |  |  | 1 | bar: WEEK 1 W
Align and evaluate stakeholders |  |  |  | 3 | bar: WEEK 1 R to WEEK 2 M
Create project charter (scope and goals) |  |  |  | 3 | bar: WEEK 2 T to WEEK 2 R
Finalize the project charter |  |  |  | 2 | bar: WEEK 2 F to WEEK 3 M
Schedule kick off meeting |  |  |  | 0.2 | bar: WEEK 2 F; WEEK 3 T
Milestone 2: Project Sourcing
Determine menu tablet specifications |  |  |  | 4
Meeting with restaurant consultant on additional tabet fetaures .To provide easy tipping option, entertaintment experience while at the table |  |  |  | 4 | `
Create contracts and statements of work for vendors |  |  |  | 2
Generate quotes and review costs |  |  |  | 3
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 0.5
Get estimate for the shipping and receiving the tablets | Mostly will get on time, unless broken shipment recieved |  |  | 10
Get the tablet content (menu and add-on coupons) | Waiting to get more information from Carter |  |  | 10
Get content to upload and mockup | Mockup are ready, just the content needs to be added |  |  | 1
Milestone 3: Tablets Installation and Testing
Schedule an electrician for wiring | since we can’t close the restaurants for a full day we need to schedule two half-days at each location |  |  | 2.5 | bar: WEEK 7 M to WEEK 7 W
Install tablets in the bar areas at the Downtown and North restaurant locations |  |  |  | 2 | bar: WEEK 7 R to WEEK 7 F
Software integration with existing POS system |  |  |  | 1 | bar: WEEK 8 M
Connect with Gilly and Contact Flatplate for software update |  |  |  | 1 | bar: WEEK 8 T
Update existing POS software version to 3.0 or higher |  |  |  | 4 | bar: WEEK 8 W to WEEK 9 M
Implement a post-dining survey to assess customer satisfaction |  |  |  | 1 | bar: WEEK 9 T
Test out the implemented service by menu tablets |  |  |  | 2 | bar: WEEK 9 T to WEEK 9 W
Schedule staff meetings with GM to discuss anything that could affect waitstaff tips |  |  |  | 1 | bar: WEEK 9 W
Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 2 | bar: WEEK 9 R to WEEK 9 F
Milestone 4: Training
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets |  |  |  | 0.1 | bar: WEEK 10 M
Schedule a training by Seydou for a small group of managers |  |  |  | 0.1 | bar: WEEK 10 M
Train the waitstaff at each location |  |  |  | 0.2 | bar: WEEK 10 T
Train the staff to update the menu |  |  |  | 0.2 | bar: WEEK 10 T
Test out the implemented service by menu tablets for final |  |  |  | 0.5 | bar: WEEK 10 W
Invite family and friends to do a test run of the tablets. |  |  |  | 0.5 | bar: WEEK 10 R
Invite family and friends to do a test run of the service. |  |  |  | 0.5 | bar: WEEK 10 F to WEEK 11 M
Launch Day |  |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Project Charter
Research data points on existing restaurant systems |  | 3 |  |  |  | H
Get historical data on ordering and payment systems of the restaurant |  | 1 |  |  |  | H
Align and evaluate stakeholders |  | 3 |  |  |  | M
Create project charter (scope and goals) |  | 3 |  |  |  | H
Finalize the project charter |  | 2 |  |  |  | H
Schedule kick off meeting |  | 0.2 |  |  |  | H
Milestone 2: Project Sourcing
Determine menu tablet specifications |  | 4 |  |  |  | M
Meeting with restaurant consultant on additional tabet fetaures .To provide easy tipping option, entertaintment experience while at the table |  | 4 |  |  |  | M
Create contracts and statements of work for vendors |  | 2 |  |  |  | M
Generate quotes and review costs |  | 3 |  |  |  | H
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 0.5 |  |  |  | H
Get estimate for the shipping and receiving the tablets | Mostly will get on time, unless broken shipment recieved | 10 | 7 | 10 | 12 | H
Get the tablet content (menu and add-on coupons) | Waiting to get more information from Carter | 10 | 7 | 10 | 14 | M
Get content to upload and mockup | Mockup are ready, just the content needs to be added | 1 | 0.5 | 1 | 2 | M
Milestone 3: Tablets Installation and Testing
Schedule an electrician for wiring | since we can’t close the restaurants for a full day we need to schedule two half-days at each location | 2.5 | 2 | 2.5 | 3 | H
Install tablets in the bar areas at the Downtown and North restaurant locations |  | 2 |  |  |  | H
Software integration with existing POS system |  | 1 | 0.4 | 0.8 | 3 | L
Connect with Gilly and Contact Flatplate for software update |  | 1 |  |  |  | H
Update existing POS software version to 3.0 or higher |  | 4 | 3 | 4 | 5 | H
Implement a post-dining survey to assess customer satisfaction |  | 1 |  |  |  | H
Test out the implemented service by menu tablets |  | 2 |  |  |  | H
Schedule staff meetings with GM to discuss anything that could affect waitstaff tips |  | 1 |  |  |  | H
Create a launch day plan: staffing, troubleshooting, etc. |  | 2 |  |  |  | H
Milestone 4: Training
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets |  | 0.1 | 0.08 | 0.2 | 2 | H
Schedule a training by Seydou for a small group of managers |  | 0.1 | 0.08 | 0.2 | 2 | M
Train the waitstaff at each location |  | 0.2 | 0.17 | 0.5 | 2 | M
Train the staff to update the menu |  | 0.2 |  |  |  | H
Test out the implemented service by menu tablets for final |  | 0.5 |  |  |  | M
Invite family and friends to do a test run of the tablets. |  | 0.5 |  |  |  | H
Invite family and friends to do a test run of the service. |  | 0.5 |  |  |  | H
Launch Day |  | 1 |  |  |  | H
|  |  | 10 | 14 | 21

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Applebee's Menu Tablets | https://www.eater.com/2017/10/5/16428750/tablet-technology-restaurants-applebees-outback-steakhouse | Oct 5,2017 | ease of tipping , server's assistance, increase in check averages
Unexpected Benefits of restaurant tablets | https://www.buzztime.com/business/5-unexpected-benefits-of-restaurant-tablets-beyond-ordering/ | N/A | create entertaining experience
Best Practices with your digital menu | https://www.barandrestaurant.com/operations/best-practices-your-digital-menu | 2022-02-23 | create categories for easier navigation

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Increase customer satisfaction by faster, more efficient experience | Average ticket time for Appetizers | What was the amount of time between placing an appetizer and delivering it to the table? | 8 minutes | þ
Increase customer satisfaction by faster, more efficient experience | Average ticket time for Entrees | What was the amount of time between placing an entree and delivering it to the table? | 12-15 minutes | þ
Increase customer satisfaction by faster, more efficient experience | Quicker check-out | Is the checkout process seamless and easy to navigate from a user perspective? | less than 1 min | þ
Increase customer satisfaction by faster, more efficient experience | Decreased wait time in lobby | Fow how many minutes is the customer waiting for being seated? | less than 10 min | þ
Tablet Experience | Technical issues | Was there any technical issue while placing the order from the tablet? | less than 5% issues | þ
Incorrect Orders | Reducing incorrect orders | Are the customer receiving correct orders as placed on the tablet ? | 98% accuarcy | þ

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for Appetizers | Are the waitstaff hearing complaints from customers concerning ticket time for Appetizers ? | 8 minutes | How long did your entire dining experience take? Please use your best judgement. | Multiple choice | Less than 30 minutes | Between 30 and 45 minutes | Between 45 minutes to 1 hour | Between 1 hour and 1.5 hours | More than 1.5 hours
Average ticket time for Entrees | Are the waitstaff hearing complaints from customers concerning ticket time for Entrees ? | 12-15 minutes | How easy was the tablet for you to use? | Multiple choice | Extremely Difficult | Difficult | Nuetral | Easy | Extremely easy
Quicker check-out | Are the customers finding the payment system quick and easy to use? | less than 1 min | Did everyone in your party receive the correct order? | Yes/No | Yes | No
Decreased wait time in lobby | Do the customers find that they have to wait too long to be seated? Does the host notice any frustration/customer leaving amongst those waiting? | less than 10 min | How long did you wait between ordering your entree and it's arrival. Please use your best judgement. | Multiple choice | Less than 5 minutes | Between 5 and 10 minutes | Between 10 and 15 minutes | More than 15 minutes | Our order never arrived. We had to ask someone.
Technical issues | Do the tablets work well and do good job with placing orders, paying and other functionalities? | less than 5% issues | How long did you wait in the lobby before being seated? | Multiple choice | 5 minutes or less | Between 5 and 10 minutes | Between 10 and 30 minutes | more than 30 minutes | I had a reservation
Order accuracy | Are customers receiving the correct orders the first time? | 98% accuarcy | Did you order any of the reccomended paired items? | Yes/No | Yes | No
|  |  | Were there any errors that occured during your dining experience? | Multiple choice | 0 errors | 1 error | 2 errors | 3 errors | 4 or more errors
|  |  | Would you reccomend dining here with the tablet experience to friends? | Yes/No | Yes | No
|  |  | Are there any other comments you have for us related to the tablet experience? If so, please let us know! | Open-ended | Open-ended
|  |  | Please rank the features of the tablet that you like from highest (1) to lowest (5). | Scaled | pairing eccomendations | the menu page | the checkout page (where you order and pay) | the games page | the featured items page
|  |  | Your checkout was quick and easy. | True/False | TRUE | FALSE